## Slide 1: Goddard Space Flight Center: Sciences and Exploration Directorate’s Virtual Machine Environment
Phillip A. Newman
August 15, 2011

## Slide 2
Code 600: Sciences and Exploration Directorate (SED)
Code 610: Earth Sciences Division
Code 660: Astrophysics Science Division
Code 670: Heliophysics Science Division
Code 690: Solar System Exploration Division
Support offices
  Code 603: Administration and Resources Management Office
  Code 605: Science Proposal Support Office
  Code 606: Computational and Information Sciences and Technology Office ( The SEDVME project is managed out of 606).
Code 700: Information Technology and Communication Directorate
  Project management help, CNE, Zoned Architecture, IT Security, Production SEDVME Service Manager
GSFC: Sciences and Exploration Directorate
Virtual Machine Environment Scorecard

## Slide 3: Goddard Space Flight Center: Sciences and Exploration Directorate’s Virtual Machine Environment (SEDVME)
The story behind SEDVME project
  What was the motivation to create the SEDVME and virtualize our servers?
  New Building Timeline: 2007 – December 2010
  How did SED approach virtualization?
  Choosing candidate servers for virtualization.
  Data Center and procurements.
  A technical description of the solution chosen.
  Project Timeline: 2008 - Present
  Success ! ? !
  Problems: Technical, Fiscal and Political/Cultural
  Questions???
GSFC: Sciences and Exploration Directorate
Virtual Machine Environment

## Slide 4: What was the motivation to create the SEDVME and virtualize our servers?
IT is getting too expensive. Consolidation will bring savings in hardware, labor, power and cooling. Virtualization will be more efficient.
Consolidation and virtualization will lead to better IT security.
Computer room space is at a premium.
The building the physical servers are in is closing. A smooth transition with little or no downtime is required when systems are moved.
The physical data center is closing and is not being replaced.
Too many webservers in SED!!
Answer: A? B? C? D? E? C,D,E&F? all of the above?
C, D, E & F

## Slide 5: SEDVME Timeline: 2007 – Dec 2010: Motivations 2007…New GSFC Science Building B34 coming…
A new science building appears in the center roadmap plan(2006)
  Supposed to accommodate 3 divisions, their labs and computers. A 4 floor state of the art green facility is planned.
  Refined requirements are still well over budget.
  Final building design reduces the building from 4 stories to a 3 story building with fewer people, fewer labs and no computer room!
Ground breaking for B34: July 16, 2007
B34 open for business September 2009
Most B2 computer rooms shutdown August 2010
B2 shutdown December 2010.

## Slide 6: Our old home Building 2
Our new home Building 34

## Slide 7: How did SED approach virtualization? Established a 600 Consolidation Committee…..
Used with permission.
copyright 2011 John Klossner, www.jklossner.com

## Slide 8: How did SED approach virtualization?
  Established a 600 Consolidation Committee…..
    Consolidate what??
      Physical location of current data centers for 660, 670 and 690 associated with move to B34. Shared data center will reside in B28 or B32.
      Storage consolidation
        Archives
        Temporary mass storage currently in labs and highbay.
        Different storage models - local vs. remote
      Web server consolidation
        Database back-ends: Sybase, MySQL, ColdFusion, others???????
        IP Load balancing…..
    What is the current “As Is” state??
      Inventory: Number of machines, physical space required, power consumption, network connectivity…….
    What is the future state??
      Shanty town(As Is) vs. “state of the art” (with virtualization or cloud technologies)
      Funding
        Startup costs
        Continual funding model
        buy in????
      Very little consensus from the committee on virtualization………………

## Slide 9: Data Center Committee Consolidation Concerns (1 of 3)
Data Center Inventory
  What has to move and to where?
    B2 to be torn down. B26 to be refurbished.
    660 & 690 go to B28. 670 goes to B21.
    Inventory of hardware and power requirements for projects slated to move to B28.
    Inventory of 600 websites.
Networking
  Procuring a data center switch.
  Procuring the wiring for sub-floor networking and patch panel
  Connection to the B2 subnet and VLANS.
  Using GSFC’s Zone Architecture Public Zone.
New Data Center Prep
  UPS
    Floor had to be reinforced with a steel beam to support the weight of the batteries
    Installation promised Dec 2008 but delivered March 2009
  Claiming the assigned space
    NCCS project took 9 months longer to finish end of life activities than expected.
IT Project management
How did SED approach virtualization?

## Slide 10: Data Center Consolidation Concerns (2 of 3)
Virtualization: Do we or don’t we?
  Risk Analysis
    IT Security concerns
      Hypervisor security?
      What is the expectation to an IRT reaction to an incident?
        All the eggs are in one basket. Will the whole thing get shutdown??
      Monitoring internal traffic.
        Suspicious activities could occur without being seen by center IT security team.
    Resource Adequacy
      Reassigning contractors to VME
    Time Constraints
      We have a hard end of July 2010 deadline to finish
    VME Maturity
    VME Experience
    Managing Growth
    Managing Acceptance
How did SED approach virtualization?

## Slide 11: Data Center Consolidation Concerns (3 of 3)
Virtualization: Do we or don’t we?
  Building a production environment vs. building a test environment.
    Contingent of committee wanted a minimal “test” investment in virtualization.
    Other committee members believe that the virtualization technologies were mature and could be immediately used to address the reduction in data center space.
  Cost
    Start up funding. Lifecycle funding?
    Hardware and licensing
    Transitioning to a virtual environment
    Dedicated system administrator labor
      Realignment and backfill of SA workforce in 660.
    Chargeback methodology
How did SED approach virtualization?

## Slide 12: Data Center Consolidation Committee Goals
Establish a virtual machine environment (VME) with a ‘standard’ infrastructure, in Building 28.
Establish an initial production environment, to support hosting of Directorate organization redesigned web pages.
Demonstrate that the VM environment can replicate or exceed current application functionality and performance.
All applications/servers must be migrated from Buildings 2 and 26 by June 2010. Where it makes sense, migrate as many of these applications as possible into the virtualized environment.
Other 600 websites to move to SEDVME after June 2010.
Define and establish SEDVME management processes and procedures.
Improve IT security – better security than the physical environment.
  Consolidated environment
  One management domain
  Standard software infrastructure
  Two-factor authentication required for all accounts.
  Accommodate Center and Agency objectives for zoning networks
How did SED approach virtualization?

## Slide 13
  Comparative analysis of virtualization technologies.
    VMware(ESX,ESXi,vSphere), Xen, PowerVM, Hyper-V
      Settled on VMware due to industry use and product maturity.
        VMotion, Storage VMotion, High Availability, vSphere
  Develop NASA Project Plan 7120.7 for SEDVME.
    SED inexperienced with a formal 7120.7 disciplines.
      Who are the reviewers???
      Hardware procured before PDR…”1st ORR” before CDR
      Science directorate website goes live just after ”1st ORR”
      Assistance from Project managers from ITCD to help with 7120.7 disciplines.
How did SED approach virtualization?

## Slide 14: Choosing candidate servers for virtualization.
Machines with low resource utilization.
  Webservers
  Database servers
  On demand request processing
Legacy servers
  Aging physical machine is due for refresh
Machines to avoid virtualization
  Any machine that has a high level of utilization more than 90% of the time.
  Machines that are heavily I/O bound or CPU bound.
  Machines that have a FIPs categorization of Medium or High.
  Machines that have high storage requirements.

## Slide 15: Data Center and VME Procurement (1 of 2)
Early in 2008, a CISCO 6509 switch is procured to be managed by the CNE network group is physically connected behind the B2 router. HEASARC storage refreshed and placed in B28.
August 2008, at the direction of the lead SED engineer, we were to procure 4 servers, UPS, and network cabling & patch panel. Out of concern that there wouldn’t be enough computing resources, 660 procured a 5th machine and Brocade FC SAN switches.
In September 2008, SED took delivery of five Dell PowerEdge R900 series machines each configured with 4 Quad core XEON E7350 Xeon, with 2.93GHz 8MB cache, 2.0Ghz, 1066MHz FSB, 128GB 32x4GB, 667MHz memory mirrored, LOM TOE NICs iSCSI ready, and two Qlogic 2460 4GB Optical Fiber cards. These machines run VMware vSphere 4.0 EA. An additional Dell running VSphere Virtual Center controls the production environment. According to VMware engineers, each physical machine should be capable of hosting 60 virtual machines for a total of 300 VMs within 5 physical boxes. We anticipate far less with our use.
August 2008, a F5 BigIP load balancer is procured to provide IP load balancing

## Slide 16
Spring 2009: SEDVME initiated a 4 year “Technology Lifecycle Management” contract with GTSI, which combined a lease to own agreement for a two 28 TB NetApp FAS 2050 filers and a 60 slot NeoStore LTO4 tape library with 4 LTO4 drives for tape backups. This contract also covers all maintenance on Dell servers, VMware, NetApp filers, BigIP and Neostore tape library.
Storage is primarily NetApp via NFS. The Netapp filers were placed in B28 and B32. The primary filer in B28 is snapmirrored to the secondary filer in B32
Data Center and VME Procurement (2 of 2)

## Slide 17
IP Load Balancing Used Heavily in 660 Web environment
Network Services – Directs network traffic requesting a service to one or several cloned VMs
  F5 Big-IP LTM (Local Traffic Manager) manages network traffic via a pair of redundant Big-IP 3400 series LTM switches
  Big-IP Fast Cache Module improves application and server performance by offloading repetitive requests for content from the backend infrastructure
  Web server pools, consisting of a number of pooled web server VMs serve as the back-end for the web sites defined on the Big-IP LTM.
A technical description
of the solution chosen. (1 of 4)

## Slide 18
A technical description
of the solution chosen. (2 of 4)

## Slide 19
A technical description
of the solution chosen. (3 of 4)

## Slide 20
A technical description
of the solution chosen. (4 of 4)

## Slide 21: SEDVME Timeline: 2008 – present. 2008…New GSFC Science Building B34 coming…
600 Data Center Consolidation
Committee Established
Cisco Router
Procured
VMware
chosen
UPS
ordered
Virtual
design
completed
VMware Training
HW procured
B2
Data
Center
Deadline
ORR 1
& SED
Website
Goes
Live
SED
Website
Development
Begins
Data
Center
Ready
UPS,
Network
Cabling,
Floor tiles
ESX
Testing
And
installation
Security
Review
ORR #2
HEASARC
Goes virtual
Catbird
Install
Server
Waiver
Process
SWIFT &
Suzaku
Pipelines
Go virtual
660
virtual
candidates
start
migration
660 & 690
Virtualized
and/or moved
Looking for new
SED business

## Slide 22: Success ! ? !
Reduced 5 racks of servers down to 1 rack.
Of 87 physical servers, 40 were virtualized and running at least as efficiently as the physical instance, 28 machines were moved, 60 machines were excessed or saved for reuse!
Cluster of 5 SEDVME machines running at an estimated 40% of capacity! Green IT…only 2 machines running full time. The 3rd spins up when the load gets high. The other 2 will spin up only when the load calls for it.
Virtualization completed on time for B2 shutdown! Minimal downtime of production servers.

## Slide 23
Significant applications virtualized!!
  High Energy Astrophysics Science Archival Research Center(HEASARC)
    Main website containing +30TB archive and data ingest systems
  Hera – server side data analysis system
  Skyview – “The Internet’s Virtual Telescope”.
  ASD websites.
  Many SSED websites.
  Swift pipeline processing.
  Suzaku pipeline processing.
Success ! ? !

## Slide 24
Problems: Technical, Fiscal and Political
Bureaucracy slows down implementation….(good and bad)
  Zone Architecture paperwork, approvals, timeliness and communication.
  Documentation requirements for each VM: SLAs, VM requests, NAMS
  Establishing, sticking to and testing the flexibility of SEDVME policy.
Catbird Security Software
  Looked EXCELLENT on paper with regard to FISMA/NIST requirements
  Catbird is unusable in it’s current state. We are hopeful that the next build will be much better or another product will need to be procured.
Storage
  I/O bottlenecks noted. Additional fast storage is needed.

## Slide 25
Problems: Technical, Fiscal and Political
Funding
  Chargeback algorithm is weak and too expensive.
  Management wants SEDVME to be self sufficient.
  Concerns about funding for new storage and other HW & SW.
Finding new customers
  Projects feel that consolidation is more expensive than building their own servers
  Projects are concerned with controlling their own servers.
  Projects are concerned about an IT security incident that could impact the entire environment.
  IT is generally listed as a “one-time acquisition” rather than a “service/utility” in Science proposals. Using the SEDVME service has an impact on funding for the science project lifecycle.
  Concerns about putting all the eggs in one basket.
  SEDVME/NASA Cloud waiver now required for all new server purchases to encourage.

## Slide 26: Questions??

## Slide 27
………..Backup Slides……….

## Slide 28
SEDVME Project Risk Matrix from PDR
Approach
M - Mitigate
W - Watch
A - Accept
R - Research
C - Close
5
4
3
2
1
1
2
3
4
5
L
I
K
E
L
I
H
O
O
D
CONSEQUENCES
Med
High
Low
Criticality
L x C Trend
Decreasing (Improving)
Increasing (Worsening)
Unchanged
New Since Last Period
New
LxC Trend | Rank | Risk ID | Approach | Risk Title
 | 1 | 06 | M | IT Security
 | 2 | 03 | M | Resource Adequacy
 | 3 | 02 | M | Time Constraint
 | 4 | 04 | M | VME Maturity
 | 5 | 05 | M | VM Experience
New New | 6 7 | 07 01 | M M | Managing growth Management Acceptance
01
02
04
05
03
New
New
New
New
New
06
07

## Slide 29: SEDVME Project Risks
Rank Risk ID Risk Statement Approach (M)
Implement access controls for each application; authorization, authority (roles), and authentication
Require RSA 2-factor authentication for VM access
Implement application IP address access control lists
Periodically run vulnerability scans (Foundstone)
Work with the GSFC IT Security Team to plan appropriate protection and incident response procedures
Provide Code 700 with VMs access to monitor the environment, including private address space
Identify VM monitoring tools that can determine the extent of an intrusion
Utilize Snap Mirror and snapshots to create backups to enable recovery
Log all interactions with centralized log host to help determine scope of intrusion
If: Any one application in the VM environment experiences an intrusion
Then: The entire VME may be taken offline
06
IT Security
Category: Technical
Expected Closure:
July 2010
1
New
Med

## Slide 30: SEDVME Project Risks
<number>
Rank Risk ID Risk Statement Approach (M)
Determine project activities, skill sets, level-of-effort, and timeframes when specific resources will be needed
Backfill FTEs that are assigned to the project
Execute Partnership Agreement with management organization(s) providing resources
Obtain commitment from Team members regarding activities and accomplishment timeframes
Allocate available resources to the prioritized list of candidate applications; re-setting the target set of applications to match available resources
Monitor team member participation and supplementing the team as necessary to address shortcomings as they arise
If: The Project’s matrixed resources are unable to devote timely and sufficient effort to establishing the VDC
Then: The VME schedule and extent of IT consolidation by July 2010 will be negatively impacted
03
Resource
Adequacy
Category: Schedule,Technical
Expected Closure:
July 2010
2
New
Med

## Slide 31
<number>
Rank Risk ID Risk Statement Approach (M)
Med
High
Low
Develop an inventory and analyze existing Code 600 applications to determine candidates for migrating to the VM environment
Establish an initial production environment, migrate SED Organization web sites, and assess performance
Prioritize and schedule candidate system migrations, concentrating on incorporating Code 660 web applications first
Work with owner organizations to obtain commitment to migrate their applications consistent with the project’s schedule
As a contingency, plan to move application servers intact, from buildings 2 and 26, to building 28 coinciding with staff moves, and migrating those applications into the VME at a later time
If: Code 660/690 applications are not migrated into the VDC in a timely manner
Then: Some candidate applications will not be absorbed into the VDC by July 2010
02
Time Constraint
Category: Schedule
Expected Closure:
July 2010
3
New
Med
SEDVME Project Risks

## Slide 32: SEDVME Project Risks
<number>
Rank Risk ID Risk Statement Approach (M)
Establish the initial production environment
Move a limited number of applications, that do not require uninterrupted service, into the VDC
Assess VME performance, then plan and implement configuration changes prior to migrating additional applications into the VDC
If: Modifications to the initial production system are needed
Then: Early VME adopters may experience a disruption in service
Notes:
The VM OS can be modified with little or no server disruption
Hardware changes could disrupt service
04
VME Maturity
Category: Technical
Expected Closure:
June 2009
4
New
Med

## Slide 33: SEDVME Project Risks
<number>
Rank Risk ID Risk Statement Approach (M)
Required that SAs be trained and VM certified prior to working with the VDC
Limited VM consulting has been funded
Require that application changes that directly interact with the VDC OS only be applied by the VDC SA staff
Plan to retain the SAs, that are gaining experience by supporting the initial VDC deployment, as part of the sustainment team
Funding is available to train an additional SA
Consider providing other staff members with a growth opportunity to be trained and provided with limited opportunities to gain experience to become potential backups
If a staff member departs, replace with an individual having VMware experience
If: The in-house staff is not experienced in VM technology
Then: The deployment may be slowed and the configuration could be inadvertently disrupted
05
VM Experience
Category: Technical
Expected Closure:
July 2009
5
New
Med

## Slide 34: SEDVME Project Risks
<number>
Rank Risk ID Risk Statement Approach (M)
Med
High
Low
Establish process for requesting/approving new VM applications
Develop a process to predict and measure actual effects of new applications accepted into the VDC
Frequently monitor system utilization; plan for capacity upgrades as necessary, and identify low usage apps as candidates for archival
Establish an annual renewal process for customers to acknowledge the continued need for their applications
Restrain growth, if necessary, to control costs and performance until the VDC is expanded to accommodate pending growth
If: The project fails to properly manage growth
Then: The VDC may become bloated with low value applications or may exceed SDC capacity
07
Managing Growth
Category: Technical
Expected Closure:
July 2010
6
New
Low

## Slide 35: SEDVME Project Risks
<number>
Rank Risk ID Risk Statement Approach (M)
Med
High
Low
Develop and execute a Stakeholder Analysis and Communications Plan
Conduct management reviews of VDC plans and progress
Establish an initial production environment, migrate SED Organization web sites, and assess performance
Present management with performance results substantiating that the VDC is viable and reliable, and can provide the same level of performance as a standalone server application
Establish a Service Level Agreement (SLA) for applications migrating into the VDC
If: Code 600 management support declines and/or the project does not receive sufficient buy-in from the Divisions
Then: Consolidation of the Code 600 IT architecture will be severely limited
01
Management Acceptance
Category: Management
Expected Closure:
July 2010
7
New
Low

## Slide 36
Host Level – Distributes VMs across multiple physical servers to gain optimal hardware utilization
VMotion is the ability to move a running VM from one ESX host to another without any interruption to the VM
Distributed Resource Scheduler (DRS) allows the cluster to be monitored continuously for even distribution of CPU and memory resources
Physical load shedding is accomplished through Virtual Center, DRS, and VMotion; scheduling VMs to fewer physical machines during non-peak times
HA (High Availability)
Fault Tolerance is accomplished by creating a live shadow instance of a VM on a second ESX host; automatically switching to the running VM should one of the ESX hosts fail
Software upgrades and patching of physical servers are accomplished on one ESX host followed by the migration of the running VM onto the upgraded ESX host, eliminating the need to disrupt VM operations
Software maintenance requiring VM downtime will be coordinated with affected users
Performance monitoring is performed automatically by VMware; system admins receive alarms and take appropriate remedial actions
Network Services – Directs network traffic requesting a service to one or several cloned VMs
F5 big-IP LTM (Local Traffic Manager) manages network traffic via a pair of redundant Big-IP 3400 series LTM switches
Big-IP Fast Cache Module improves application and server performance by offloading repetitive requests for content from the backend infrastructure
Web server pools, consisting of a number of pooled web server VMs serve as the back-end for the web sites defined on the Big-IP LTM
Load Balancing

## Slide 37: IT Security
Adherance to Agency mandated IT security controls (such as Patchlink and CIS)
Patching VMs accomplished via Redhat satellite server
Export control of NFS shares
  VMDK share is defined within the VM
  LDAP defined netgroups to centralize authorization
Public services are placed in a Zoned Architecture Public Zone
NAMS authorization to set up VM
Local LDAP to authorize access to individual applications
2-factor authentication required for VME access
Firewalls and access control lists (ACLs) at choke points
Access Control Lists (ACLs) between VMs via Catbird
Centralized logging of all VMs via Virtual Center, syslog, and Catbird
Catbird controls, logs and tracks configuration changes
Centralized logging via Catbird and Hypervisor
Scanning provided by Foundstone appliance managed by Code 700

## Slide 38: Catbird Security Capabilities
Catbird V-Agents provide a full spectrum of security services in a virtual environment.
Catbird V-Agents monitor, protect, scan, inventory and quarantine at Network Layer2. Catbird administrator places physical and virtual elements in TrustZones by category.
Complementary architecture to virtualized environments
  Stateless: scan be turned off and moved around w/no side effects
  Can ONLY be managed centrally, no local console or services that can be compromised
Continuous hacker protection both in and out of the hypervisor
  IDS/IPS
  Rogue User
  Vulnerability scanning
  Credentialed and Policy Monitoring

## Slide 39: SEDVME Configuration with Catbird

## Slide 40: Authorization and Authentication Approach
Authorization
  Information about the VME will be entered into NATT
  The NAMS workflow will be used to authorize user access to the VME environment
  The local VME LDAP will control access to individual systems/applications in the VME environment, residing on the Virtual Machine and on stand-alone servers
  VME users are identified by AUID
Authentication
  The VME will use RSA tokens to provide 2-factor authentication of users
  The VME RSA tokens have been integrated into the Code 700 RSA structure
  When available, the VME RSA tokens will be integrated into the Agency RSA token system

## Slide 41: SEDVME Access
All public web applications will be accessed through the Center’s Zoned Architecture Public Zone
  Firewall rules for both inbound and outbound traffic
  VMs will not be dually connected
  All public IP services will change IP addresses to 129.164.179.#
  VMs will not be placed on the Center’s Zoned Architecture Public Zone subnet
  Login access to public servers will be restricted
ACLs controlled from Catbird, limits communicating to hosts as requirements dictate.
LDAP controls the environment. Netgroups will restrict logins to hosts
Two factor RSA required on all VMs
Access to physical hardware on the private management network will be through a dually connected physical hardened host that requires two factor RSA. This will allow an SSH tunnel through this host to Virtual Center.